## Tab 1 Project Design
TEMPLATE 3 Tab 1: PROJECT DESIGN STATEMENT - RFPS-NYH-2021-503374
Company name: |  | Cirrolytix Research Services - Project AEDES
Note: it is mandatory to complete columns C-F for each Activity you propose. Incomplete project designs will not be scored.
Timeline |  | Tasks | Expected Changes/Targets | Signs of Success | Key Personnel Responsible
|  | What are the major milestones you will achieve with the UNICEF Innovation Fund investment? Which activities do you need to do to achieve each milestone? Adjust the number of milestones and activities for each quarter as needed. | What will be different once the activity is done? (Provide specific numbers where possible.) | What will you measure/look at to assess if you completed the activity? And whether you achieved your desired outcome? Please specify the numeric values of your desired outcomes [ie.number of users]. Each activity must have at least one. | Which team member is responsible for each task? Refer to the funding agreement for the definition of 'Key Personnel" and who can be included on this list.
Quarter 1
| Milestone 1 | Team Formation and Kickoff |  |  | Project Lead
| Activity 1 | Finalize team skill requirements | Skills requirements document | Completed skills requirements document | Project Lead
| Activity 2 | Role design | Organization design document | Completed organizational design document | Project Lead
| Activity 3 | Promote job openings | Posted job openings | Published job openings | Project Lead
| Activity 4 | Recruit team members | Signed contracts | Signed contracts | Project Lead
| Activity 5 | Onboarding and debriefing | Team onboarding session | Team onboarding session conducted | Project Lead
| Milestone 2 | Automate data gathering |  |  | Data Engineer
| Activity 1 | Finalize automation requirements | Automation requirements document | Completed requirements document | Data Engineer, Geospatial Analyst
| Activity 2 | Automation design - Remote Sensing | Automation design document | Completed design document | Geospatial Analyst
| Activity 3 | Automation design - google trends | Automation design document | Completed design document | Data Engineer
| Activity 4 | Automation design - weather | Automation design document | Completed design document | Data Engineer
| Activity 5 | Automation design - dengue cases and deaths | Automation design document | Completed design document | Data Engineer
| Activity 6 | Implement automation - Remote Sensing | Automation implementation | Completed automation document | Data Engineer, Geospatial Analyst
| Activity 7 | Implement automation - Google Trends | Automation implementation | Completed automation document | Data Engineer
| Activity 8 | Implement automation - weather | Automation implementation | Completed automation document | Data Engineer
| Activity 9 | Implmeent automation - dengue cases and deaths | Automation implementation | Completed automation document | Data Engineer
| Activity 10 | Automation testing and evaluation | Test scripts and feedback | Successfully completed test | Data Engineer, Geospatial Analyst, Project Lead
Quarter 2
| Milestone 3 | Enhance nowcasting models |  |  | Data Scientist
| Activity 1 | Finalize nowcasting requirements | Nowcasting requirements document | Requirements document completed | Data Scientist, Project Lead
| Activity 2 | Nowcasting design | Nowcasting design document | Design document completed | Data Scientist, Data Engineer, Geospatial Analyst
| Activity 3 | Data gathering - dengue cases and deaths | Dengue case dataset | Dataset gathered | Data Scientist, Data Engineer, Geospatial Analyst
| Activity 4 | Data gathering - google trends | Google trends dataset | Dataset gathered
| Activity 5 | Data gathering - weather data | Weather dataset | Dataset gathered
| Activity 6 | Nowcasting modeling - linear regression | Linear model | Linear model draft completed | Data Scientist
| Activity 7 | Nowcasting modeling - time-series | Time-series model | Time-series model draft completed | Data Scientist
| Activity 8 | Nowcasting modeling - SVM | SVM model | SVM model draft completed | Data Scientist
| Activity 9 | Nowcasting testing and evaluation | Test scripts and feedback | Successful test completed | Data Scientist, Data Engineer, Geospatial Analyst, Project Lead
| Activity 10 | Nowcasting model deployment | Deployed model/s | Model deployed | Data Scientist
| Milestone 4 | Enhance mosquito hotspot detection model
| Activity 1 | Finalize hotspot detection requirements | Hotspot requirements document | Requirements document completed | Data Scientist, Geospatial Analyst
| Activity 2 | Hotspot detection design | Design document | Design document completed | Data Scientist, Geospatial Analyst
| Activity 3 | Data gathering - remote sensing | Remote sensing dataset | Dataset gathered | Data Scientist, Geospatial Analyst, Data Engineer
| Activity 4 | Data gathering - ground observations | Ground observations dataset | Dataset gathered | Data Scientist, Geospatial Analyst
| Activity 5 | Hotspot modeling | Hotspot model | Hotspot model draft completed | Data Scientist
| Activity 6 | Hotspot model testing and evaluation | Test scripts and feedback | Successful test completed | Data Scientist, Geospatial Analyst
| Activity 7 | Hotspot model deployment | Deployed model | Model deployed | Data Scientist, Geospatial Analyst
Quarter 3
| Milestone 5 | Web / mobile portal development and enhancement | Portal requirements document | Requirements document completed
| Activity 1 | Finalize web and mobile portal requirements | Portal design document | Design document completed | Application Developer, Project Lead
| Activity 2 | Web and mobile portal design and wireframes | Wireframe completed | Wireframes completed | Application Developer
| Activity 3 | Web and mobile portal development | Alpha platform | Alpha platform released | Application Developer
| Activity 4 | Web and mobile portal testing and evaluation | Beta platform, Test Scripts | Beta platform released and test scripts successfully completed | Application Developer, Project Lead
| Activity 5 | Web and mobile portal go-live | Live platform | Live platform released
| Milestone 6 | Implement INFORM Risk Framework
| Activity 1 | Finalize risk requirements | Risk requirements document | Requirements document completed | Project Lead, Data Scientist
| Activity 2 | Risk framework design | Risk framework design | Framework design document completed | Project Lead, Data Scientist
| Activity 3 | INFORM inputs data gathering | Risk datasets | Risk datasets gathered | Project Lead, Data Engineer
| Activity 4 | Implement INFORM Risk Framework | Risk calculations | Draft risk calculations completed | Data Scientist, Data Engineer, Application Developer, Geospatial Analyst
| Activity 5 | Risk Framework testing and evaluation | Test scripts and feedback | Test scripts successfully completed | Data Scientist, Data Engineer, Application Developer, Geospatial Analyst
| Activity 6 | INFORM model deployment | INFORM page on platform | INFORM page implemented on platform | Data Engineer, Application Developer
Quarter 4
| Milestone 7 | Recruit consumers
| Activity 1 | Finalize target consumers | Target consumer list | Target consumer list generated | Project Lead
| Activity 2 | Business development plan | Business development plan | Business development plan completed | Project Lead
| Activity 3 | Promote platform | Conduct promotion | 1 completed promotion | Application Developer, Project Lead
| Activity 4 | Recruit consumers | Prospects identified | At least 1 prospect identified | Project Lead
| Activity 5 | Onboarding and debriefing | Customer onboarded | At least 1 customer onboarded | Project Lead
| Activity 6 | Support and maintenance | Ongoing customer support | At least 1 customer query answered | Data Engineer, Application Developer
| Milestone 8 | Publication and dissemination
| Activity 1 | Finalize publication requirements | Publication requirements document | Requirements document completed | Project Lead, Data Scientist
| Activity 2 | Publication plan and design | Publication plan | Publication outline completed | Project Lead, Data Scientist
| Activity 3 | Manuscript drafting and development | Manuscript draft | At least 1 manuscript draft completed | Project Lead, Data Scientist
| Activity 4 | Editing and feedback | Completed manuscript | 1 research paper manuscript | Project Lead, Data Scientist
| Activity 5 | Publication | Published manuscript | 1 research paper published | All
| Activity 6 | Webinar and training | Conducted webinar | At least 1 public webinar conducted | All
Note on C5: ====== ID#AAAAQmha61Y Anne Reyes (2021-10-04 14:46:35) Please make sure complete texts are captured within a cell by wrapping the text and adjusting the row height and/or column width of the cell
Note on D5: ====== ID#AAAAQmha61U Anne Reyes (2021-10-04 14:46:35) Please make sure complete texts are captured within a cell by wrapping the text and adjusting the row height and/or column width of the cell
Note on E5: ====== ID#AAAAQmha61Q Anne Reyes (2021-10-04 14:46:35) Please make sure complete texts are captured within a cell by wrapping the text and adjusting the row height and/or column width of the cell

## Tab 2 Data Plan
TEMPLATE 3 Tab 2: DATA PLAN - RFPS-NYH-2021-503374
Company name: |  | Cirrolytix Research Services - Project AEDES
Timeline |  | Tasks | What data will be generated during the project? | Source of Data
|  | Each project will be completing major milestones and activities, as defined in template 3, tab 1 (the Project Design). Please use the same milestones and activities for this templates. Relevant cells are linked to tab 1 and will replicate this information for you. If you added or deleted any rows in tab 1, please make sure that they are replicated on this sheet. | Each phase will generate some data. For example: (1) while you are developing a software solutions, there will be "commits" on GitHub; while you are developing new content, the volume of online data will increase. (2) while you are piloting a solution, you can track user numbers or user feedback; edits/updates to code or designs (3) while you are using a solution, you can track new users; deployment progress through an online tracker We require each phase to have real-time data that is accessible via Internet protocols linked to it. | For each kind of data mentioned in column D, provide the source of the data (e.g. a link to a GitHub repository). If the data doesn't exist yet, please explain in this column and indicate in the timeline when it will be made available.
Quarter 1
| Milestone 1 | Team Formation and Kickoff
| Activity 1 | Finalize team skill requirements
| Activity 2 | Role design
| Activity 3 | Promote job openings | Job applications generated | CVs
| Activity 4 | Recruit team members | Role Metrics | Project Management
| Activity 5 | Onboarding and debriefing | Tracker | Project Management
| Milestone 2 | Automate data gathering
| Activity 1 | Finalize automation requirements
| Activity 2 | Automation design - Remote Sensing
| Activity 3 | Automation design - google trends
| Activity 4 | Automation design - weather
| Activity 5 | Automation design - dengue cases and deaths
| Activity 6 | Implement automation - Remote Sensing | Commits | Github
| Activity 7 | Implement automation - Google Trends | Commits | Github
| Activity 8 | Implement automation - weather | Commits | Github
| Activity 9 | Implmeent automation - dengue cases and deaths | Commits | Github
| Activity 10 | Automation testing and evaluation
Quarter 2
| Milestone 3 | Enhance nowcasting models
| Activity 1 | Finalize nowcasting requirements
| Activity 2 | Nowcasting design
| Activity 3 | Data gathering - dengue cases and deaths | Dengue case data | DOH Epidemiology Bureau
| Activity 4 | Data gathering - google trends | Google trends | Google
| Activity 5 | Data gathering - weather data | Temperature and precipitation data | DOST-PAGASA Weather bureau
| Activity 6 | Nowcasting modeling - linear regression | Commits, predictions | Github, Model
| Activity 7 | Nowcasting modeling - time-series | Commits, predictions | Github, Model
| Activity 8 | Nowcasting modeling - SVM | Commits, predictions | Github, Model
| Activity 9 | Nowcasting testing and evaluation
| Activity 10 | Nowcasting model deployment
| Milestone 4 | Enhance mosquito hotspot detection model
| Activity 1 | Finalize hotspot detection requirements | latlongs
| Activity 2 | Hotspot detection design
| Activity 3 | Data gathering - remote sensing | commits, latlongs, remote sensing readings | Github, Remote sensing
| Activity 4 | Data gathering - ground observations | commits, latlongs, ground observations | Github, Ground observation
| Activity 5 | Hotspot modeling | commits, latlongs, predictions
| Activity 6 | Hotspot model testing and evaluation | Metrics | Model
| Activity 7 | Hotspot model deployment
Quarter 3
| Milestone 5 | Web / mobile portal development and enhancement
| Activity 1 | Finalize web and mobile portal requirements
| Activity 2 | Web and mobile portal design and wireframes
| Activity 3 | Web and mobile portal development
| Activity 4 | Web and mobile portal testing and evaluation
| Activity 5 | Web and mobile portal go-live | Usage statistics | Google analytics
| Milestone 6 | Implement INFORM Risk Framework
| Activity 1 | Finalize risk requirements
| Activity 2 | Risk framework design
| Activity 3 | INFORM inputs data gathering
| Activity 4 | Implement INFORM Risk Framework | Index | Model
| Activity 5 | Risk Framework testing and evaluation
| Activity 6 | INFORM model deployment
Quarter 4
| Milestone 7 | Recruit consumers | Impressions | FB Marketing
| Activity 1 | Finalize target consumers
| Activity 2 | Business development plan
| Activity 3 | Promote platform | Impressions | FB Marketing
| Activity 4 | Recruit consumers | Impressions | FB Marketing
| Activity 5 | Onboarding and debriefing
| Activity 6 | Support and maintenance
| Milestone 8 | Publication and dissemination | Reader count | Research site
| Activity 1 | Finalize publication requirements
| Activity 2 | Publication plan and design | Reader count | Research site
| Activity 3 | Manuscript drafting and development | Reader count | Research site
| Activity 4 | Editing and feedback
| Activity 5 | Publication | Reader count | Research site
| Activity 6 | Webinar and training | Attendees | Webinar Recordings
Note on C4: ====== ID#AAAAQmha61M Anne Reyes (2021-10-04 14:46:35) Please make sure complete texts are captured within a cell by wrapping the text and adjusting the row height and/or column width of the cell
Note on D4: ====== ID#AAAAQmha61I Anne Reyes (2021-10-04 14:46:35) Please make sure complete texts are captured within a cell by wrapping the text and adjusting the row height and/or column width of the cell